## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
PB1 | Flight Search |  | As a user, I want to search flights by source, destination, and date | MUST HAVE | Flight database schema | Backend Team | 3- Completed
PB2 | Flight Data |  | As a system, I want to store flight, airline, and airport data | MUST HAVE | None | Backend Team | 3- Completed
PB3 | Dynamic Pricing |  | As a user, I want to see prices change based on demand and availability | MUST HAVE | Flight search API | Backend Team | 3- Completed
PB4 | Booking |  | As a user, I want to book a seat on a flight | MUST HAVE | Dynamic pricing engine | Backend Team | 3- Completed
PB5 | Concurrency |  | As a system, I want to prevent double booking of seats | MUST HAVE | Booking workflow | Backend Team | 2- In Progress
PB6 | Cancellation |  | As a user, I want to cancel my booking | SHOULD HAVE | Booking workflow | Backend Team | 2- In Progress
PB7 | Frontend UI |  | As a user, I want a simple UI to search and book flights | SHOULD HAVE | Backend APIs | Frontend Team | 3- Completed
PB8 | Receipts |  | As a user, I want to download booking receipts | COULD HAVE | Booking confirmation | Frontend Team | 2- In Progress

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-01-07 | 14-07-2025 | Backend Developer | Start documenting DB schema decisions | Stop last-minute schema changes | Continue daily code reviews | Created finalized database ER diagram and shared with team
2 | Sprint 1 | 2025-01-07 | 14-07-2025 | Frontend Developer | Start early UI wireframing | Stop waiting for full backend completion | Continue requirement discussions | Prepared UI mockups in advance for integration
3 | Sprint 2 | 15-07-2025 | 28-07-2025 | Backend Developer | Start modular pricing logic | Stop hardcoding pricing values | Continue incremental testing | Refactored pricing engine into reusable functions
4 | Sprint 2 | 15-07-2025 | 28-07-2025 | Backend Developer | Start logging price changes | Stop ignoring edge cases | Continue demand simulation | Added logging for price fluctuations
5 | Sprint 3 | 29-07-2025 | 2025-11-08 | Backend Developer | Start transaction-based booking | Stop testing without concurrency | Continue API validation | Implemented database transactions and seat locking
6 | Sprint 3 | 29-07-2025 | 2025-11-08 | Backend Developer | Start UUID-based PNR generation | Stop sequential PNR creation | Continue booking workflow testing | Integrated UUID for unique PNRs
7 | Sprint 4 | 2025-12-08 | 25-08-2025 | Frontend Developer | Start UI performance optimization | Stop overloading single API calls | Continue frontend-backend sync | Optimized API calls and added loaders
8 | Sprint 4 | 2025-12-08 | 25-08-2025 | QA / Tester | Start end-to-end testing | Stop late bug reporting | Continue regression testing | Fixed UI and booking flow issues before final delivery

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 1 | Initial database schema confusion | Reviewed project requirements and finalized schema design
Sprint 1 | Day 2 | None | Continued API development as planned
Sprint 1 | Day 3 | Data validation issues | Added input validation and error handling
Sprint 2 | Day 9 | Complexity in pricing rules | Simplified pricing logic into modular functions
Sprint 2 | Day 12 | Demand simulation inconsistency | Adjusted demand simulation parameters
Sprint 3 | Day 18 | Concurrency handling uncertainty | Used database transactions and locking mechanism
Sprint 3 | Day 26 | PNR generation conflicts | Implemented UUID-based PNR generation
Sprint 4 | Day 28 | API response delay in UI | Optimized API calls and added loading states
Sprint 4 | Day 34 | Minor UI bugs | Fixed CSS and JavaScript validation issues